American Samoa Disaster Relief Effort Timeline

Nov. 24, 2009		Letter sent to Governor

Dec. 4, 2009		Ad ran in newspaper requesting fishermen to report losses

Dec. 11, 2009		14 reports received by AS coordinator and sent to Council staff

Dec. 18, 2009 		Ad being distributed to the outer villages by DMWR samplers

Dec. 10-Jan. 25	15 additional reports received by AS coordinator and sent to Council staff

Jan 13, 2010	DMWR report on damages sent to Council

Jan 15-16, 2010	Missing inventory list received from Longline Services

Dec- Jan 2010	Package being prepared for Governor’s office by Council staff

Jan.27, 2010	Complete package including 5 copies sent to Governor’s office (1st one) and the letter was e-mailed

Feb. 13, 2010	EK and KS met with the Governor in Pago Pago

Feb. 26, 2010	Revised package completed

Mar 1, 2010	Revised package sent FedEx to Governor including evaluation and proposal and Feb photos (2nd one)

Mar 3, 2010	Revised letter e-mailed to Governor’s office (2nd one)

March 9, 2010	Governor’s office sent e-mail saying they received package and would send us a copy of the signed letter

Apr 5, 2010	E-mail sent to Governor’s office inquiring about the status of the package—no reply

Apr 7, 2010	E-mail sent to NMFS HQ contact Abigail Franklin asking if they received package

Apr 8, 2010	NMFS replied not yet and that they’d send a copy when they did