Fisheries Disaster Relief Program

Introduction

- Alton Miyasaka open the meeting at 10 a.m.

- Introductions were made. Present were Mark Mitsuyasu, Craig Severance, Paul Bartram, David Itano, Gary Dill, Kurt Kawamoto, Mike Fujimoto, Chris Boggs Earl Miyamoto.

Program Review

- Review project information

- Historical background

- State of Hawaii proposal and distribution of funds.

- Review program budget and admin changes.

- Reviewed previous correspondence with NOAA regarding grant and award conditions.

ESC (executive steering committee)

- Reviewed the esc and actions to date.

TWG

- Reviewed membership

- Craig suggested pursuing kalthoff

- Itano offered to follow up with rivera

Legal notice

- Alton reviewed the legal notice.

- Itano asked if a letter of intent was going to be sent out first before the rfp.

- Pfrp uses the two tier model.

- Use the first review to help identify which fishermen need further assistance.

- Craig severance supported the two tier process

- We are talking about the 1.5 mil for DLNR to fund.

- Weight the funding priorty to those most impacted.

- Earl is looking for a follow on meeting to set the criteria.

- Chris; current legal notice sounds like it is for the 5 mill. Do we need to separate the process.

- Need to add letter of intent and full proposal language.

- Include that JIMAR will be coming out with a grant for the other 3 million.

- Dave itano; one page legal notice. Then a call for proposals that lists the separate programs.

- Chris; two legal notices; one for letter of interest; other for full proposals.

- Timing should be one month for the letter of intent.

- Timing should take longer if they do a two tier process.

- Guidelines for letter of intent should be short.

- Funds will not be for purchase of their boat.

- Legal notice should have contact reference to website; if include criteria, where would we need to put that in. does it get approved by esc.

- One month full proposal is too short. Need to consider longer.

- Plan to get all the money out on first crack. If no good proposals, then go out with second.

- Don’t give extensions to proposals.

- Late august be letter of intent due date august 26.

- Ask for full proposals by late October.

- 2 weeks evaluation of letter of intent.

- Proposals due November 15.

- Awards by January 15.

- Revised text. Please indicate where your proposals is to be directed – cooperative agreement vs. fishery support.

- Provide guidance about the amount of funding per proposal.

- Guideline to project ceiling; but amounts up to certain amount may be considered.

- Assistance to individuals (1000s), assistance to organizations (100K), and research and development (1000s to 100K). Amounts will be considered based on economic benefits.

- Gary dill; legal defense fund, promotion program; marketing campaign

- A suggested range for proposal budget is up to 20K for individual fishermen, 100K for groups and associations that include a group of fishermen and potentially larger amounts for cooperative research. Somewhat larger amounts will be considered for worthy projects.

- The program will consider funding individual project proposals in the range of about 20-30 K; funding of projects in excess of 100K may be considered for larger scale cooperative research projects of benefit to broader sector of federally impacted fisheries.

- Paragraph B;  your letters should indicate weather funding is directed for direct economic federal assistance (e.g. gear replacement, vessel modification or other cost of compliance) or for cooperative fisheries research and development (e.g.  development of markets, alterative fisheries, or new techniques to mitigate bycatch).